## SCPP - Supplier Rollout Plan
Rollout: Supply Chain Performance Program Purchasing
Location | Plant | 2021-06-01 |  |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  |  | 2022-04-01 |  |  |  | May 22 |  |  |  | 2022-06-01
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Europe | bar: 25 to 2021-07-01 28
Schweinfurt | SWE | bar: 26 to 2021-07-01 28; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Höchstadt | HMS | bar: 2021-07-01 27 to 2021-07-01 29; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Lahr | IWL | bar: 2021-10-01 40 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Steinhagen | ELG | bar: 2021-07-01 28 to 2021-07-01 30; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Homburg | ILH | bar: 2021-08-01 32 to 2021-08-01 34; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Herzogenaurach | IWS | bar: 2021-08-01 32 to 2021-08-01 34; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Caldas da Rainha | FRC | bar: 2021-08-01 32 to 2021-08-01 34; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Debrecen | FAH | bar: 2021-08-01 32 to 2021-08-01 34; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Haguenau | ILF | bar: 2021-08-01 32 to 2021-08-01 34; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Brasov | ISB | bar: 2021-07-01 27 to 2021-07-01 29; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Kysucke | IWK | bar: 2021-07-01 28 to 2021-07-01 30; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Skalica | ILS | bar: 2021-07-01 28 to 2021-07-01 30; 2021-10-01 42 to 2021-12-01 51; 2022-01-01 2 to 2022-01-01 3
Americas | bar: 25; 2021-11-01 46 to 2022-03-01 13
Sorocaba | IB1 | bar: 2021-10-01 43 to 2022-01-01 4
Joplin | FAJ | bar: 2021-10-01 43 to 2021-12-01 51
Asia / Pacific | bar: 25; 2021-11-01 46 to 2022-03-01 13
Vietnam | SVC | bar: 2021-10-01 43 to 2021-12-01 52
Changwon | FHS | bar: 2021-10-01 43 to 2022-02-01 8
Pune | IBI | bar: 2021-10-01 43 to 2022-02-01 8
Baroda | FBI | bar: 2021-10-01 43 to 2022-02-01 8
Savli | SFI | bar: 2021-10-01 43 to 2022-02-01 8
Greater China | bar: 25; 2021-10-01 40 to 2022-02-01 8
Nanjing | SNM | bar: 2021-10-01 42 to 2022-01-01 2
Yinchuan | FXR | bar: 2021-10-01 42 to 2022-01-01 2
Legend: |  | Supplier information letter about Supply Chain Performance Program
Supplier web site available (with relevant information material)
Supplier information letter about packaging data updates
Supplier specific info about missing packaging data sheets for each plant
Guideline how to fill out the packaging data sheet
Process description for the updates of packaging information
Start query to get updated replenishment lead times (RLT) from all suppliers for all components
Start SupplyOn integration (WebEDI/EDI; ASN; GTL; Performance Monitor)
Rollout & signing of Industrial Supply Agreement*
Supplier specific component overview with new classification, expected delivery lead time, current & future fixed horizon
Training material for suppliers to understand details of the Supply Agreement are available (in Englisch and Chinese)
*) a supplier to multiple plants will typically be contacted only once (timing dependent upon the plant with the earliest need to get the Supply Agreement in place)

## SCPP - Production Rollout Plan
Rollout: Supply Chain Performance Program per Plant/Segment
Plant | Location | Plant No. | Segment | Comment | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  |  | 2022-07-01 |  |  |  | 2022-08-01
[5 empty] | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Europe
SWE | Schweinfurt | 0200 | Segment 04 | completed
|  |  | Segment 12 | current plan | bar: 2021-11-01 44 to 2021-11-01 47
|  |  | Segment 06 | current plan | bar: 2021-11-01 47 to 2022-02-01 8
|  |  | Segment 11 | current plan | bar: 2022-02-01 7 to 2022-05-01 20
HMS | Höchstadt | 0072 | Segment 04 | current plan | bar: 2021-11-01 44 to 2022-01-01 3
|  |  | Segment 03 | current plan | bar: 2021-12-01 48 to 2022-02-01 5
IWL | Lahr | 0002 | Segment 01 | current plan | bar: 2021-11-01 44 to 2022-01-01 4
|  |  | Segment 04 | current plan | bar: 2021-11-01 44 to 2022-02-01 7
ELG | Steinhagen | 0012 | Segment 02 | current plan | bar: 2022-01-01 2 to 2022-03-01 12
IWS | Herzogenaurach | 0061 | Segment 01 | current plan | bar: 2022-04-01 15 to 2022-06-01 26
FRC | Caldas da Rainha | 0254 | Segment 02 | current plan | bar: 2021-11-01 47 to 2022-04-01 14
FAH | Debrecen | 0236 | Segment 03 | current plan | bar: 2021-11-01 47 to 2022-02-01 8
ISB | Brasov | 0097 | Segment 21 | current plan | bar: 2021-11-01 44 to 2021-11-01 47
|  |  | Segment 24 | current plan | bar: 2021-11-01 47 to 2022-01-01 4
|  |  | Segment 06 | current plan | bar: 2021-11-01 47 to 2022-02-01 7
|  |  | Segment 01 | current plan | bar: 2021-11-01 45 to 2021-12-01 49
|  |  | Segment 08 | current plan | bar: 2022-03-01 13 to 2022-04-01 17
|  |  | Segment 10 | current plan | bar: 2022-02-01 8 to 2022-03-01 12
|  |  | Segment 16 | current plan | bar: 2022-02-01 8 to 2022-04-01 17
|  |  | Segment 20 | current plan | bar: 2022-05-01 18 to 2022-06-01 22
IWK | Kysucké Nové Mesto | 0045 | Segment 01 | current plan | bar: 2022-01-01 2 to 2022-04-01 14
ILS | Skalica | 0095 | Segment 01 | current plan | bar: 2022-01-01 2 to 2022-04-01 14
|  |  | Segment 04 | current plan | bar: 2022-02-01 6 to 2022-05-01 21
|  |  | Segment 10 | current plan | bar: 2022-03-01 10 to 2022-06-01 25
ILH | Homburg (Saar) | 0009 | Segment 01 | bar: 2022-03-01 11 to 2022-06-01 26
ILF | Haguenau | 0087 | Segment 02 | bar: 2022-03-01 11 to 2022-06-01 26
Americas
IB1 | Sorocaba | 0701 | Segment 32 | preliminary plan | bar: 2022-03-01 10 to 2022-06-01 26
FAJ | Joplin | 0275 | Segment 01 | preliminary plan | bar: 2021-12-01 51 to 2022-03-01 9
|  |  | Segment 02 | preliminary plan | bar: 2022-02-01 6 to 2022-05-01 18
|  |  | Segment 04 | preliminary plan | bar: 2022-03-01 11 to 2022-06-01 23
|  |  | Segment 05 | preliminary plan | bar: 2022-03-01 11 to 2022-05-01 18
Asia / Pacific
SVC | Vietnam | 0358 | Segment 01 | preliminary plan | bar: 2021-12-01 51 to 2022-03-01 9
|  |  | Segment 02 | preliminary plan | bar: 2022-02-01 6 to 2022-05-01 18
|  |  | Segment 03 | preliminary plan | bar: 2022-02-01 6 to 2022-05-01 18
FHS | Changwon | 0297 | Segment 06 | preliminary plan | bar: 2022-03-01 9 to 2022-05-01 21
IBI | Pune | 0042 | Segment 02 | preliminary plan | bar: 2022-04-01 14 to 2022-07-01 29
FBI | Baroda | 0295 | Segment 02 | preliminary plan | bar: 2022-02-01 5 to 2022-05-01 20
|  |  | Segment 04 | preliminary plan | bar: 2022-03-01 9 to 2022-06-01 24
|  |  | Segment 05 | preliminary plan | bar: 2022-03-01 13 to 2022-07-01 28
|  |  | Segment 08 | preliminary plan | bar: 2022-04-01 17 to 2022-08-01 32
SFI | Savli | 8210 | Segment 01 | preliminary plan | bar: 2022-02-01 5 to 2022-06-01 22
|  |  | Segment 02 | preliminary plan | bar: 2022-03-01 11 to 2022-06-01 26
|  |  | Segment 05 | preliminary plan | bar: 2022-04-01 15 to 2022-07-01 30
|  |  | Segment 08 | preliminary plan | bar: 2022-05-01 19 to 2022-08-01 31
Greater China
SCT | Taicang | 8101 | Segment 24 | Segment 24 | bar: 2022-03-01 9 to 2022-04-01 16
SNM | Nanjing | 8111 | Segment 05 | preliminary plan | bar: 2021-12-01 51 to 2022-03-01 12
|  |  | Segment 06 | preliminary plan | bar: 2022-01-01 1 to 2022-03-01 13
|  |  | Segment 07 | preliminary plan | bar: 2022-01-01 1 to 2022-02-01 8
|  |  | Segment 10 | preliminary plan | bar: 2022-02-01 6 to 2022-03-01 13
|  |  | Segment 11 | preliminary plan | bar: 2022-02-01 6 to 2022-03-01 13
|  |  | Segment 42 | preliminary plan | bar: 2022-03-01 10 to 2022-04-01 17
|  |  | Segment 43 | preliminary plan | bar: 2022-03-01 10 to 2022-04-01 17
|  |  | Segment 45 | preliminary plan | bar: 2022-04-01 14 to 2022-05-01 21
|  |  | Segment 46 | preliminary plan | bar: 2022-04-01 14 to 2022-05-01 21
FXR | Yinchuan | 0289 | Segment 02 | preliminary plan | bar: 2022-03-01 9 to 2022-04-01 15